## README
SEA Seller Sourcing — Cold-Start Execution Tracker
Week 2 (Sep 1–7) · 9.9 sprint prep · generated Wed 2 Sep 2026
HOW TO USE THIS FILE
1. Every tab is a live working log, not a template. Fill the shaded orange cells; black cells are formulas — do not overwrite them.
2. One row per asset / per community / per campaign / per day. Add rows by copying the last row down so formulas carry.
3. Daily standup: read the 'Daily Dashboard' tab. Alert thresholds are conditional-formatted; anything that turns red needs an intervention that day.
4. Weekly review: 'Funnel & Attribution' + 'Budget & Burn' are the two tabs to bring to the Friday retro.
5. Figures marked [ASSUMPTION] in the Growth Kit pages are starting targets, not measured reality. Replace them with your own numbers by Sep 14.
TAB INDEX
Daily Dashboard — north-star funnel + alert thresholds, auto-calculated
Weekly Review — CAC / activation / retention by week, targets vs actual
Content Log — what shipped, on which channel, with the result
Community Outreach Log — every group/forum/Telegram-WhatsApp touch + outcome
Paid Ads Launch Board — campaign-level build & daily spend state
Lifecycle Tracker — email + WhatsApp/Telegram sends and response rates
Referral & KOC Tracker — invites sent/accepted, partner pipeline, payouts
Offline BD Log — walk-ins, market districts, partner meetings, QR scans
Case Study Pipeline — sellers to interview, status, permission, publish date
UTM Campaign Registry — the only allowed campaign names (prevents dirty data)
Budget & Burn — committed vs actual spend by channel and week
SEO & Localization Backlog — page build queue with language status
Risk Register — early signal, mitigation, owner, kill-switch rule
LEGEND
Orange fill = you type here
Grey/white = formula or label, leave alone
Red text in a metric cell = threshold breached, act today
NOTE ON FORMULAS
Metric columns (rates, CPA/CAC, the Decision and Alerts columns, TOTAL rows) are live formulas. They show blank until you fill the orange input cells, then compute on open in Excel / WPS / LibreOffice. Verify rates appear after you type the first row of numbers.
Targets such as CAC <= $3.00 and activation >= 45% are starting assumptions taken from the Growth Kit, not measured benchmarks. Replace the thresholds once you have 2-3 weeks of own data.

## Daily Dashboard
Daily Dashboard
Type the shaded cells only. Signup rate = signups/sessions; activation = first search / signups; CPA = paid spend / signups. Targets by Sep 14: signup rate 4–6%, activation ≥45%, CPA ≤$3 [ASSUMPTION].
Date | Sessions | Signups | First search | Results saved | Supplier contacts | Paid spend (USD) | Organic+social signups | Signup rate | Signup→first-search % | CPA (USD) | Alerts
2026-09-01
2026-09-02
2026-09-03
2026-09-04
2026-09-05
2026-09-06
2026-09-07
2026-09-08
2026-09-09
2026-09-10
2026-09-11
2026-09-12
2026-09-13
2026-09-14
2026-09-15
TOTAL

## Weekly Review
Weekly Review
Weekly retro input. Retention = users still searching 7 days after signup. All target CAC values are [ASSUMPTION] starting points until 3 weeks of own data exist.
Week | Focus | Sessions | Signups | First search | Day-7 retained | Paid spend | CAC | Signup→search | 7-day retention | Target CAC | Verdict
W2 Sep 1–7 | Content volume + FB group cold start | [8 empty] | $3.00 [ASSUMPTION]
W3 Sep 8–14 | 9.9 sprint + paid live (Sep 8) + AMA | [8 empty] | $3.50
W4 Sep 15–21 | Retro + 11.11 pre-heat + lifecycle | [8 empty] | $3.00
W5 Sep 22–28 | SEO + referral loop + localization | [8 empty] | $2.50
W6 Sep 29–Oct 5 | 11.11 pre-heat ramp + partner/KOC | [8 empty] | $2.50

## Content Log
Content Log
One row per shipped asset. 'Repurposed into' is the discipline check — an asset with one use is a wasted production hour.
Date | Asset | Format | Funnel stage | Primary channel | Repurposed into | Views | Clicks | Signups | Status | Owner | Note / lesson
2026-09-02 | Hot Picks Weekly Ranking — Top 10 for 9.9 | Article + collage | Awareness | Site + FB groups | 12 short-video scripts, 5 LinkedIn posts |  |  |  | done | Content | Wednesday flagship slot
2026-09-03 | Supplier Spotlight — #1 category teardown | Article | Consideration | Site + Telegram | Reels part 1 |  |  |  | scheduled | Content | Origin belt + MOQ tiers
2026-09-04 | 9.9 Sourcing Asset Pack | Lead magnet | Capture | All + FB groups | Email 1 of the 6-email sequence |  |  |  | scheduled | Growth | Comment FREE + form, max 4 fields
2026-09-05 | 3 red-flag supplier check shorts | Video x3 | Awareness | TikTok / Reels | Quora answers |  |  |  | scheduled | Content | Spark Ads candidates
2026-09-06 | Weekend group poll + AMA teaser | Discussion | Engagement | FB groups + own group | AMA promo copy |  |  |  | scheduled | Community | Weekend ritual
2026-09-07 | 9.9 countdown + margin calculator push | Tool + posts | Conversion | Email + WhatsApp + all | Pinned group post |  |  |  | planned | Growth | Tool page = tool/index.html
2026-09-08 | Live AMA 'Stock for 9.9 in 30 min' | Live | Conversion | FB + Telegram | 6 clips for W4 |  |  |  | planned | Both | Paid ads go live same day
2026-09-09 | 9.9 day-of: 'what to stock today' | Article + posts | Conversion | All | Day-after recap |  |  |  | planned | Content | Free window framing must be real

## Community Outreach Log
Community Outreach Log
Log every cold-start community touch. If a platform has no row for a day, that platform did not happen — this tab is the accountability mechanism for W2.
Date | Platform | Community / subreddit / group name | Country | Size | Post or comment | Replies | Profile clicks | DMs sent | DM→signup | Group joins earned | Removed/banned? | Owner | Next action
2026-09-02 | Facebook Group | Shopee Malaysia Sellers | MY |  | Hot Picks as discussion post |  |  | 10 |  |  | no | Community | Reply sweep 3pm
2026-09-02 | Facebook Group | Lazada Indonesia Seller Community | ID |  | Value comments only (warm-up) | [5 empty] | no | Community | Post Thursday
2026-09-02 | Telegram | VN cross-border seller channels | VN |  | Comment + DM script |  |  | 5 |  |  | no | Community | Localize to VI
2026-09-03 | WhatsApp Community | ID modest-wear sellers | ID |  | Asset pack offer | [5 empty] | no | Community | Max 4 touches / 10 days
2026-09-03 | Reddit | r/ecommerce, r/dropship, r/Shopee | Global |  | Answer sourcing questions, no link | [5 empty] | no | Content | Build karma first
2026-09-04 | Forum | Pantip (TH) / Kaskus (ID) / Lowyat (MY) | TH/ID/MY |  | Localized value post | [5 empty] | no | Community | Needs TH reviewer

## Paid Ads Launch Board
Paid Ads Launch Board
9 campaigns = USD 60/day (paid go-live Mon Sep 8). CTR/CPC/CPA and the Decision column are formulas. CPA kill thresholds come from the Paid Media page of the Growth Kit and are [ASSUMPTION] until 50+ conversions per ad set.
Channel | Campaign name | Market | Objective | Daily budget (USD) | Status | Impr. | Clicks | CTR | CPC | Signups | CPA | First-search rate | Decision | Date decision
Meta | meta_ID_sales_lal-signups_99selection_20260908 | ID | Sales (signup) | 10 | draft
Meta | meta_SEA_sales_broad_sellers_99selection_20260908 | PH/MY/TH | Sales (signup) | 8 | draft
Meta | meta_SEA_lead_interest-sellers_pricemoq_20260908 | All SEA | Lead (Instant Form) | 5 | draft
Meta | meta_SEA_retarget_sales_warm-loop_20260908 | All SEA | Sales (retarget) | 3 | draft
Google | sea_search_supplier-intent_99 | All SEA (en/id/th/vi) | Signups | 8 | draft
Google | sea_search_99-seasonal | All SEA | Signups | 6 | draft
Google | sea_search_alternative-intent | All SEA | Signups | 4 | draft
TikTok | tiktok_sea_spark_hotpicks_20260908 | ID/VN/PH/TH | Video views → retarget | 10 | draft
Test | reserve_experiments_rotating | rotating | learning | 6 | draft

## Lifecycle Tracker
Lifecycle Tracker
Open/click/reply rates are industry-dependent — set your own baseline in week 1, then compare to yourself, not to benchmarks.
Date | Flow | Segment | Message / subject | Sent | Delivered | Open rate | Click rate | Replies | Signups | Unsub / blocked | Deliverability note | Fix applied
2026-09-04 | Email | Asset-pack leads | Here's your 9.9 Sourcing Asset Pack
2026-09-05 | Email | Asset-pack leads | The 3 mistakes before 9.9
2026-09-06 | WhatsApp | Opted-in ID/MY sellers | Day-2 nudge (max 4 touches / 10 days) | [7 empty] | throttle 20/hr per number
2026-09-07 | Email | All leads | 9.9 eve — free window closes
2026-09-09 | Email + WhatsApp | Active + lapsed | Day-of: what to stock today
2026-09-10 | Email | 9.9 buyers | Results + 11.11 pre-heat invite

## Referral & KOC Tracker
Referral & KOC Tracker
Placeholder rows in square brackets must be replaced with real names before outreach — do not send a partner pitch to an unnamed account.
Date | Type | Partner / referrer | Channel they post on | Audience size | Code / link | Invites sent | Signups | First searches | Credits paid (USD) | Status | Next step
| KOC | [seller-training account] | TikTok |  | KOC001 |  |  |  |  | contacted | Send brief + free credits
| KOC | [ERP / seller-tool account] | Telegram |  | KOC002 |  |  |  |  | contacted | Bundle offer
| Affiliate | [sourcing agent / forwarder] | WhatsApp |  | AGT001 |  |  |  |  | qualified | Rate card + tracking code
| Referral | [early user] | own group |  | REF001 |  |  |  |  | active | Check 72h activation

## Offline BD Log
Offline BD Log
Offline sellers are in the target definition but had zero motion. Target from Sep 8: 20 logged visits/week; measure by QR scans, not goodwill.
Date | City / market district | Seller type | Contact name | Channel (walk-in/Whats App/referral) | Demo given? | Signups | QR scans on one-pager | Partner lead? | Follow-up due | Notes
| [verify district before visiting] | phone accessories stall |  | walk-in | yes |  |  | no |  | 30-second pitch + assisted signup
| [verify] | wholesale distributor |  | referral | no |  |  | yes |  | book meeting, bring margin sheet

## Case Study Pipeline
Case Study Pipeline
Social proof caps conversion on every other channel. 5 stories before Sep 8. No fabricated numbers, no invented testimonials — the result cell must be seller-confirmed in writing.
Seller / shop | Platform | Country | Category | Headline result [must be verified] | Interview done | Written permission | Assets collected | Story drafted | Published | Reuse spots
[5 empty] | no | no |  | no | no | Hero + ad + group post

## UTM Campaign Registry
UTM Campaign Registry
Only these names may appear in links. Anything not on this list gets pasted into the wrong GA4 row and costs you the retro.
Allowed campaign name | Source | Medium | Content/creative | Term | Channel owner | Registered in GA4?
w2_content_hotpicks | organic | social | collage-v1 | hotpicks | Content | no
w2_groups_coldstart | facebook | community | group-post-v1 | 99 | Community | no
w2_assetpack | site | leadgen | pack-cover-v1 | assetpack | Growth | no
w3_pre_99_meta | meta | paid_social | sellers-15s | 99 | Growth | no
w3_pre_99_google | google | cpc | rsa-a | supplier | Growth | no
w3_pre_99_tiktok | tiktok | paid_social | spark-hotpicks | 99 | Content | no
w3_sea_99_meta-id | meta | paid_social | id-local-v1 | 99 | Growth | no
w3_ama_live | facebook | event | ama-promo | ama | Community | no
w3_offline_qr | offline | qr | onepager-v1 | walkin | BD | no
w3_referral_loop | in-product | referral | wa-share-v1 | credits | Growth | no
w4_seo_longtail | google | organic | n/a | category | Content | no
w4_1111_preheat | site | email | bootcamp-invite | 1111 | Lifecycle | no

## Budget & Burn
Budget & Burn
Committed figures are the plan (USD 60/day for W3 = 420, plus non-media line items). Actual = what really got spent. Cash discipline: never ramp a channel that has not hit its own CPA target for 3 consecutive days.
Week | Channel | Committed (USD) | Actual (USD) | % of total | Signups | Cost/signup | Variance | Comment
W3 Sep 8–14 | Meta | 182
W3 Sep 8–14 | Google | 126
W3 Sep 8–14 | TikTok | 70
W3 Sep 8–14 | Test reserve | 42
W3 Sep 8–14 | Offline/one-pagers (print) | 60
W3 Sep 8–14 | Community (contests/credits) | 90
W4 Sep 15–21 | Meta | 300
W4 Sep 15–21 | Google | 200
W4 Sep 15–21 | TikTok | 120
W4 Sep 15–21 | Partners/KOC credits | 150
W4 Sep 15–21 | Localization (native reviewers) | 200
W4 Sep 15–21 | Community | 90
W5 Sep 22–28 | Meta | 350
W5 Sep 22–28 | Google | 250
W5 Sep 22–28 | TikTok | 150
W5 Sep 22–28 | SEO content | 250
W5 Sep 22–28 | Offline events | 150
W5 Sep 22–28 | Partners/KOC | 150
TOTAL

## SEO & Localization Backlog
SEO & Localization Backlog
SEO is the compounding channel the original plan omitted. Volume estimates intentionally left blank — verify in Search Console, do not paste guessed volumes.
Priority | Page / cluster | URL pattern | Language | Keyword target | Template ready | Built | Indexed | Ranking | Owner | Note
P0 | Category sourcing hub (top 10 categories) | /sourcing/[category]-supplier-[country] | en | supplier intent | yes | no | no |  | Content | Feeds Meta + Google landing pages
P0 | Bulk-buying long tail | /where-to-buy/[product]-bulk-[platform] | en | platform+product bulk | no | no | no |  | Content | Programmatic template
P1 | 9.9 / 11.11 event pages | /sales/9-9-[platform]-sourcing | en | seasonal | no | no | no |  | Content | Refresh annually
P1 | Tool pages | /tools/99-margin-calculator | en | price/MOQ/negotiation | yes | yes | no |  | Growth | Live as tool/ in this kit
P2 | ID localization of top 20 pages | same path + /id/ | id | supplier intent | no | no | no |  | Localization | Native review required
P2 | VI + TH localization | same path + /vi/ /th/ | vi, th | supplier + bulk | no | no | no |  | Localization | After ID proves out

## Risk Register
Risk Register
Every risk has a trip-wire so the decision is made by data, not by mood in week 3.
Risk | Channel | Early signal | Likelihood | Impact | Mitigation | Owner | Kill-switch rule
WhatsApp number banned for bulk messaging | Lifecycle | Delivery drops, blocks >2% | medium | high | Opt-in only, throttle, human handoff, rotate to Telegram | Lifecycle | Blocks >5% → stop broadcasts 7 days
Meta ad account disabled | Paid | Rejected ads, policy warnings | medium | high | Clean policy copy, no unrealistic earnings claims, verified domain, backup BM | Growth | Second rejection → pause spend, appeal first
Removed as spam by group admins | Community | Deleted posts, bans | high | medium | Value-first ladder, 1 post/group/week, admin permission where required | Community | 3 removals on one platform → rewrite approach
CAC exceeds contribution margin | Paid | CPA > $4 for 3 days | medium | high | Cut scale, hold best ad set only, fix LP before buying more traffic | Growth | CPA > $6.50 blended → kill the channel for the week
Supplier data quality complaints | Product | Tickets, wrong price/MOQ | medium | high | Mark estimates vs verified, feedback capture in results view, weekly data cleanup | Product | Complaint rate >10% → pause paid scale
English-only ceiling | All | ID/TH/VN signups stall | high | medium | Localize ad copy + top 20 pages, native reviewers | Localization | If localized CPA <70% of EN → shift budget
9.9 window too short to convert | Lifecycle | Signups with no first search | medium | medium | Onboarding to first search in one session; bridge offer into 11.11 | Both | If 7-day activation <25%, stop discount-led messaging
Cash/burn without signal | Finance | Spend up, retention flat | medium | high | Weekly budget review, no ramp before 3 green days | Owner | Day-10 spend with <50 first searches → cut to 50%
Messaging consent / PDPA exposure | Lifecycle | Complaints, opt-out spikes | low | high | Explicit opt-in, consent line per country, verify with counsel | Ops | Any complaint → pause that flow, review consent record